Radiogram No. 2800 u											for 01.25.02

EVA-6		January 25, 2002

ISS-4:	EV1 – Yuri Onufrienko		EV2 – Dan Bursch	IV – Carl Walz

EXTRAVEHICULAR ACTIVITY TIMELINE

Installation of СКК№1-DC, installation of PLATAN-M payload, installation of СКК№2-SM, installation of ГЗУ plume deflectors, retrieval of KROMKA1-0 payload, installation of KROMKA1 payload, installation of СКК№1-SM, installation of WA4 Ham Radio Antenna

| No. | Operator | Task Description | Duration (minutes) | GMT | DMT |
| --- | --- | --- | --- | --- | --- |
| Orbital Night |  |  | 15:09 – 15:43 (18:09 – 18:43) |  |  |
| 1 | EV1 | Open EV hatch 1 (ОВЛ1) | :06 | 15:35 -15:41 | 18:35 -18:41 |
| 2 | EV1 | Install protective ring (ЗК) | :03 | 15:44 | 18:44 |
| 3 | EV1 | Egress DC | :04 | 15:48 | 18:48 |
| 4 | EV1; EV2 | Transfer EVA cluster №1 (Plume Deflectors (ГЗУ) + Ham Radio Antenna WA4) onto EV Ladder (ВУ) | :03 | 15:51 | 18:51 |
| 5 | EV1; EV2 | Transfer EVA cluster №2 (EVA Tool Carrier (КПУ) + small frame + KROMKA 1 payload + Semi-rigid airtight container (ПГК) + СКК№1-SM + СКК№2-SM + PLATAN-M payload + СКК№1-DC) onto EV Ladder (ВУ) | :03 | 15:54 | 18:54 |
| 6 | EV2 | Egress DC | :02 | 15:56 | 18:56 |
| 7 | EV1 | Separate СКК№1-DC from EVA cluster №2 and transfer it along HRs 3030 and 3031 to HR3032 | :02 | 15:58 | 18:58 |
| 8 | EV1 | Install СКК№1-DC on HR3032 (secure lock with wire tie), remove protective cover, deploy and take photos | :05 | 16:03 | 19:03 |
| 9 | EV1 | Translate onto EV Ladder (ВУ) along HR3031 & 3030, secure protective cover of СКК№1-DC near EV Hatch 1 (ВЛ1) | :01 | 16:04 | 19:04 |
| 10 | EV2; EV1 | Combine EVA clusters №1 & №2 into single cluster | :01 | 16:05 | 19:05 |
| 11 | EV1; EV2 | Transfer combined EVA cluster along EV Ladder gap spanner (ФПД ВУ), HRs 2313, 2314, 2315, 2316, 2317, 2318, 2411 to HR2411 | :06 | 16:11 | 19:11 |
| 12 | EV1; EV2 | Separate PLATAN-M from combined EVA cluster and transfer it along HRs 2443, 2442, 2441, 2434, 2435, 2433 to HR2433 | :06 | 16:17 | 19:17 |
| 13 | EV1; EV2 | Install PLATAN-M (secure lock with wire tie) on HR2433, deploy and take photos | :05 | 16:22 | 19:22 |
| 14 | EV1; EV2 | Translate to combined EVA cluster along HRs 2433, 2435, 2434, 2441, 2442, 2443 to HR2411 (if necessary, wait for attitude thruster inhibit and, if time allows, visually inspect and take photos of Window 7 area) | :05 | 16:27 | 19:27 |
| 15 | EV1; EV2 | Translate combined EVA cluster along HRs 2411, gap spanner (ФПД) on SM РО2 cone, HRs 2511, 2541 | :02 | 16:29 | 19:29 |
| 16 | EV2 | Separate Fairlead-1 from combined EVA cluster and install it on HR 2541 (next to standoff closest to ПхО) | :02 | 16:31 | 19:31 |
| 17 | EV2; EV1 | Translate combined EVA cluster along HRs 2512, 2542, 2611, 2647 to HRs 2611 & 2647 on SM Assembly Compartment (АО) | :02 | 16:33 | 19:33 |
| 18 | EV1; EV2 | Separate СКК№2-SM from combined EVA cluster, transfer it along HRs 2646, 2645, 2644, 2746. 2745, install (secure lock with wire tie) on HR2745, remove protective cover, deploy and take photos if possible, return to combined EVA cluster and attach protective cover to КПУ | - :07 | 16:40 | 19:40 |
| 19 | EV2 | Separate Fairlead-2 from combined EVA cluster and install it on HR 2646 (next to standoff between HR2646 and HR2647) | :02 | 16:42 | 19:42 |
| Orbital Night (crew rest) |  |  | 16:42 – 17:15 (19:42 – 20:15) |  |  |
| 20 | EV1; EV2 | Split combined EVA cluster, secure EVA cluster №2 on HR2647 by the КПУ lock, secure EVA cluster №1 on HR2646 and HR2612 | :04 | 17:19 | 20:19 |
| 21 | EV1; EV2 | Separate ГЗУ ”РIV” from EVA cluster №1, install and take photos | - :09 | 17:28 | 20:28 |
| 22 | EV1; EV2 | Separate bundle ГЗУ ”КI”,”ТI” + Antenna WA4 from EVA cluster, transfer it along HRs 2645, 2644, 2643, 2642, 2641, and secure on HR2641 | - :06 | 17:34 | 20:34 |
| 23 | EV1; EV2 | Install Antenna WA4 with 6 cable clamps on HR2642 (secure antenna lock with wire tie) | :04 | 17:38 | 20:38 |
| 24 | EV1; EV2 | Translate along HRs 2643, 2644, 2645, 2648, separate from clusters and transfer bundle ГЗУ ”РII” + ПГК along HRs 2648, 2613, 2614, 2615, 2616, 2619, 2623, 2618, 2622, 2624 (wipe HRs 2614 & 2615 with towel) | - :11 | 17:49 | 20:49 |
| 25 | EV2; EV1 | Remove KROMKA1-0 from HR2624 and place it into ПГК, secure ПГК with KROMKA1-0 on HR2622 | - :06 | 17:55 | 20:55 |
| 26 | EV1; EV2 | Install ГЗУ ”РII” and take photos (if possible) | - :09 | 18:04 | 21:04 |
| 27 | EV2; EV1 | Transfer ПГК with KROMKA1-0 along HRs 2622, 2618, 2623, 2619, 2616, 2615, 2614, 2613, 2648, and attach it to КПУ | :08 | 18:12 | 21:12 |
| 28 | EV2; EV1 | Separate ГЗУ ”ТI” from ГЗУ ”КI” | :02 | 18:14 | 21:14 |
| Orbital Night (crew rest) |  |  | 18:14 – 18:48 (21:14 – 21:48) |  |  |
| 29 | EV1; EV2 | Transfer ГЗУ ”КI” and ”ТI” along HRs 2613, 2614, take photos of installation area | :04 | 18:52 | 21:52 |
| 30 | EV1; EV2 | Install ГЗУ ”ТI” | :06 | 18:58 | 21:58 |
| 31 | EV1; EV2 | Install ГЗУ ”КI”, wipe ORLAN gloves with towel | :09 | 19:07 | 22:07 |
| 32 | EV1; EV2 | Separate KROMKA1 from EVA cluster №2, remove protective cover, install, and secure it on collapsible HR of ГЗУ ”ТI”, take photos of KROMKA1 and ГЗУ ”КI” & ”ТI” | :06 | 19:13 | 22:13 |
| 33 | EV1; EV2 | Translate to bundle ГЗУ ”КIII” + ”ТIII” along HRs 2613, 2648, 2645, 2644, 2643, 2642, 2641 | - :07 | 19:20 | 22:20 |
| 34 | EV1; EV2 | Separate ГЗУ ”ТIII” from ГЗУ ”КIII”, transfer it along HRs 2634, 2633 (wipe HRs 2633, 2635 and 2632 with towel), take photos of installation area of ГЗУ ”КIII” & ”ТIII” | - :05 | 19:25 | 22:25 |
| 35 | EV1; EV2 | Install ГЗУ ”ТIII” | - :06 | 19:31 | 22:31 |
| 36 | EV1; EV2 | Install ГЗУ ”КIII”, wipe ORLAN gloves with towel, take photos of ГЗУ ”КIII” and ”ТIII” | :09 | 19:40 | 22:40 |
| 37 | EV1; EV2 | Install cable clamps in openings labeled ”11”, ”12”, ”13”, and ”14”, and on HR2641 (install cable clamp 6 (backup) in opening labeled ”16”) | :10 | 19:50 | 22:50 |
| Orbital Night (crew rest) |  |  | 19:47 – 20:20 (22:46 – 23:20) |  |  |
| 38 | EV1; EV2 | Route and place Antenna WA4 cable into the cable clamps, mate connectors ХФП11-4, secure cable slack, check installation of Antenna WA3, use additional wire tie to secure antenna if necessary | :09 | 20:29 | 23:29 |
| 39 | EV1; EV2 | Take photos of the open ФП11 connector plate, slacked cable, cable clamps with routed cable, closed ФП11 connector plate, Ham Radio Antennas WA3 & WA4 | :06 | 20:35 | 23:35 |
| 40 | EV1; EV2 | Translate along HRs 2633, 2634, 2641, 2643, 2644, 2645, 2648, 2646 to EVA cluster №2 | :05 | 20:40 | 23:40 |
| 41 | EV1 | Separate СКК№1-SM from EVA cluster №2, install it on HR2611 (secure lock with wire tie), remove protective cover and deploy, take photos, attach protective cover on КПУ | :06 | 20:46 | 23:46 |
| 42 | EV1; EV2 | - Translate with bundle (КПУ + small frame + ПГК with KROMKA1-0) along HRs 2646, 2612, 2611, 2647, 2542, 2512, 2541, 2511, gap spanner (ФПД) on SM РО2 cone, and HR2411 to HR2411 | :07 | 20:53 | 23:53 |
| 43 | EV1; EV2 | - Visually inspect and, if possible, take photos of Window 7 area | :06 | 20:59 | 23:59 |
| 44 | EV1; EV2 | Translate to DC EV hatch 1 with bundle (КПУ + small frame + ПГК with KROMKA1-0) along HRs 2318, 2317, 2316, 2315, 2314, 2313 and DC EV Ladder | :04 | 20:03 | 23:03 |
| 45 | EV2 | Ingress DC | :02 | 20:05 | 23:05 |
| 46 | EV2 | Transfer bundle (КПУ + small frame + ПГК with KROMKA1-0) and protective cover of СКК№1-DC into DC-1 | :02 | 21:07 | 00:07 |
| 47 | EV2 | Ingress DC | :03 | 21:10 | 00:10 |
| 46 | EV2 | Remove protective ring (ЗК) | :03 | 21:13 | 00:13 |
| 47 | EV2 | Close EV hatch 1 (ЗВЛ) | :06 | 21:19 | 00:19 |
| Orbital Night |  |  | 21:19 – 21:52 (00:19 – 00:52) |  |  |

Total EVA duration: 5 hours 44 minutes

End of radiogram